## User stories
| Main User Story | Sub-Task
1 | Admin | Add Asset
Update Asset
Delete Asset
Get Assets By Id/Name
Get All Assets
View AssetForms
Allocate Asset
Reject Request
Get All Allocations
2 | Manager | Raise Requests
Check Status of Request
Get All Employees
Get Employee by Id/Name
Add Employees
Update Employee
Delete Employee
3 | Authentication | Login

## Abhishek
Task No. | Task Name | Estimated Hours/Time | Actual Time Taken | Allotted on Day
1 | Asset
1.1 | Configuring Properties and Database | 1.5 | 1.5 | 2020-06-06
1.2 | Add Asset
1.2.1 | Service | 1.5 | 1.5 | 2020-06-06
1.2.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.2.3 | Testing | 2 | 2 | 2020-06-10
1.3 | Update Asset
1.3.1 | Service | 1.5 | 1.5 | 2020-06-06
1.3.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.3.3 | Testing | 2 | 2 | 2020-06-10
1.4 | Delete Asset
1.4.1 | Service | 1 | 1 | 2020-06-06
1.4.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.4.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.5 | Get All Assets
1.5.1 | Service | 1 | 1 | 2020-06-06
1.5.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.5.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.6 | Get Asset by Id
1.6.1 | Service | 1 | 1 | 2020-06-08
1.6.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.6.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.7 | Get Asset by Name
1.7.1 | Service | 1 | 1 | 2020-06-08
1.7.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.7.3 | Testing | 1.5 | 1.5 | 2020-06-10
2 | Authentication
2.1 | Configuring Properties and Database | 1.5 | 1.5 | 2020-06-08
2.2 | Login
2.2.1 | Service | 1.5 | 1.5 | 2020-06-08
2.2.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
2.2.3 | Testing | 2 | 2 | 2020-06-10
3 | Asset Management Consumer
3.1 | Controller | 2 | 2 | 2020-06-09
3.2 | Testing | 3 | 3 | 2020-06-10

## Samiran
Task No. | Task Name | Estimated Hours/Time | Actual Time Taken | Allotted on Day
1 | AssetForm
1.1 | Configuring Properties and Database | 1.5 | 1.5 | 2020-06-06
1.2 | Add AssetForm
1.2.1 | Service | 1.5 | 1.5 | 2020-06-06
1.2.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.2.3 | Testing | 2 | 2 | 2020-06-10
1.3 | Allocate
1.3.1 | Service | 1 | 1 | 2020-06-06
1.3.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.3.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.4 | Reject | ]
1.4.1 | Service | 1 | 1 | 2020-06-06
1.4.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.4.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.5 | Get All AssetForm
1.5.1 | Service | 1 | 1 | 2020-06-06
1.5.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.5.3 | Testing | 1.5 | 1.5 | 2020-06-10
2 | AssetAllocation
2.1 | Configuring Properties and Database | 1.5 | 1.5 | 2020-06-08
2.2 | Add AssetAllocation
2.2.1 | Service | 1.5 | 1.5 | 2020-06-08
2.2.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
2.2.3 | Testing | 2 | 2 | 2020-06-10
2.3 | Get All Asset Allocation
2.3.1 | Service | 1 | 1 | 2020-06-08
2.3.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
2.3.3 | Testing | 1.5 | 1.5 | 2020-06-10
3 | Asset Management Consumer
3.1 | Controller | 2 | 2 | 2020-06-09
3.2 | Testing | 3 | 3 | 2020-06-10

## Amarsinh
Task No. | Task Name | Estimated Hours/Time | Actual Time Taken | Allotted on Day
1 | Employee
1.1 | Configuring Properties and Database | 1.5 | 1.5 | 2020-06-06
1.2 | Add Employee
1.2.1 | Service | 1.5 | 1.5 | 2020-06-06
1.2.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.2.3 | Testing | 2 | 2 | 2020-06-10
1.3 | Update Employee
1.3.1 | Service | 1 | 1 | 2020-06-06
1.3.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.3.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.4 | Delete Employee
1.4.1 | Service | 1 | 1 | 2020-06-06
1.4.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.4.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.5 | Get All Employee
1.5.1 | Service | 1.5 | 1.5 | 2020-06-08
1.5.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.5.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.6 | Get Employee by Id
1.6.1 | Service | 1.5 | 1.5 | 2020-06-08
1.6.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.6.3 | Testing | 1.5 | 1.5 | 2020-06-10
1.7 | Get Employee by Name
1.7.1 | Service | 1.5 | 1.5 | 2020-06-08
1.7.2 | Validations + Exception Handling | 1 | 1 | 2020-06-09
1.7.3 | Testing | 1.5 | 1.5 | 2020-06-10
2 | Asset Management Consumer
2.1 | Controller | 2 | 2 | 2020-06-09
2.2 | Testing | 3 | 3 | 2020-06-10